## Cover
FSAM UAT – Disaster Recovery Scenario Matrix
Phase 1 – Infrastructure ¦ Steps 1–9b ¦ Azure Infra Team
Step | Resource | Sheet | # Scenarios
1 | Recovery Services Vault | RSV | 6
2 | Key Vault – Secrets & Access | KeyVault | 6
3 | Storage Account – Backup | Storage | 5
4 | Virtual Network / NSGs / NICs | Network | 6
5+6 | VM OS Disk C:\ + Data Disk E:\ | VM_Disks | 7
7 | Load Balancer | LoadBalancer | 5
8 | SSL Certificate | SSL_Certificate | 5
9 | Monitoring & Alerting | Monitoring | 5
9b | External Connectivity | External | 4

## RSV
DR Scenario Matrix – Recovery Services Vault (fsamuat-rsv)
Step 1 ¦ Backup: Azure Backup built-in RSV ¦ Freq: N/A Pre-check ¦ Dep: None – DR Start
# | Disaster Scenario | Severity | Likelihood | Impact | Detection Method | Terraform DR Action | Manual Steps (if any) | RTO Target | Runbook Dep
1 | RSV accidentally deleted from portal | Critical | Low | All VM and SQL DB backup history lost; no restore points available | VM heartbeat alert fires; az backup vault show returns 404 | terraform apply recreates fsamuat-rsv with GRS + soft-delete. Re-registers VM and SQL DB backup items. | DBA must verify sfam_uat_db backup items re-appear. Trigger manual backup job immediately. | 0.2 hrs | None – DR Start
2 | RSV soft-deleted (within 14-day retention window) | High | Medium | Vault appears missing in portal but backup data still retained for 14 days | terraform plan shows RSV missing; portal shows soft-deleted state | provider.features.recovery_services_vault.recover_soft_deleted = false — run: az resource invoke-action --action recoverSoftDeleted, then terraform apply | Confirm vault returns to Active state before next backup job runs. | 0.2 hrs | None – DR Start
3 | Backup replication changed from GRS to LRS | High | Medium | Loss of geo-redundancy; backup data not replicated to secondary region | Azure Policy compliance alert; az backup vault backup-properties show returns LRS | terraform apply enforces storage_mode_type = GeoRedundant on existing RSV | None – Terraform corrects drift automatically. | 10 min | None – DR Start
4 | Backup Operator RBAC removed from DR operator | Medium | High | DR operator cannot trigger restore jobs during disaster event | DR operator gets 403 when running az backup restore commands | terraform apply re-creates azurerm_role_assignment.dr_operator_backup_operator | None – Terraform corrects drift automatically. | 5 min | None – DR Start
5 | Backup job for sfam_uat_db fails repeatedly | High | Medium | RPO gap grows; latest restore point becomes stale | rsv-backup-job-failure alert fires to infra-ag action group | Alert fires automatically. No Terraform action — investigate SQL agent on VM. | DBA checks SQL Server Agent job logs on fsam-uat-vm. Retry backup manually via portal. | 1 hr | None – DR Start
6 | RSV soft-delete disabled by admin | Critical | Low | RSV can be permanently deleted with no recovery window | Azure Policy non-compliance alert; terraform plan shows drift | terraform apply re-enables soft_delete_enabled = true on RSV resource | None – Terraform corrects drift automatically. | 5 min | None – DR Start
SEVERITY LEGEND
Critical
High
Medium
Low

## KeyVault
DR Scenario Matrix – Key Vault (fsamuat-kvprivatebmw)
Step 2 ¦ Backup: Soft-delete + purge-protection ¦ Freq: Continuous ¦ Dep: Step 1
# | Disaster Scenario | Severity | Likelihood | Impact | Detection Method | Terraform DR Action | Manual Steps (if any) | RTO Target | Runbook Dep
1 | Key Vault fsamuat-kvprivatebmw accidentally deleted | Critical | Low | SQL SA password and DB connection strings inaccessible; app cannot connect to DB | kv-availability-drop alert fires; app throws 503 / DB connection errors | provider auto-recovers soft-deleted KV on next terraform apply (recover_soft_deleted_key_vaults=true) | If hard-purged: DBA must re-populate sql-sa-password and db-connection-string secrets manually after KV recreated. | 0.3 hrs | Step 1
2 | KV purge-protection disabled — vault at risk of permanent deletion | Critical | Low | KV can be hard-purged with no recovery; secrets permanently lost | terraform plan shows drift on purge_protection_enabled | terraform apply re-enables purge_protection_enabled = true | None – Terraform corrects drift automatically. | 5 min | Step 1
3 | Managed Identity role assignment removed — app loses KV access | High | High | App cannot retrieve DB connection string; all DB operations fail | App logs show 403 Forbidden on KV secret fetch; kv-availability alert fires | terraform apply re-creates azurerm_role_assignment.app_mi_kv_secrets_user (Key Vault Secrets User) | Restart app service / IIS app pool after role propagation (~2 min). | 10 min | Step 1
4 | Private Endpoint fsamuat-kvprivatebmw-pe disconnected | High | Medium | KV unreachable from VM via private network; public access is denied | PE connection state != Approved; Invoke-RestMethod from VM returns timeout | terraform apply re-creates azurerm_private_endpoint.kv_pe with auto-approval | Verify PE DNS resolution: Resolve-DnsName fsamuat-kvprivatebmw.vault.azure.net from VM. | 20 min | Step 1
5 | KV secret sql-sa-password deleted or expired | Critical | Medium | Application cannot authenticate to SQL Server; full service outage | App DB connection errors; KV audit logs show secret access failure | Terraform manages secret slot with ignore_changes=[value]. Slot recreated by terraform apply if missing. | DBA must set the actual secret value: az keyvault secret set --vault-name fsamuat-kvprivatebmw --name sql-sa-password --value <pwd> | 15 min | Step 1
6 | KV geo-redundant replication disrupted | High | Low | KV unavailable in primary region with no failover to secondary | kv-availability-drop metric alert fires; Portal shows KV degraded | KV geo-redundancy is platform-managed (not configurable via TF). Alert fires automatically. | Open Azure support ticket. Monitor Azure Service Health for region outage updates. | Dep on Azure | Step 1
SEVERITY LEGEND
Critical
High
Medium
Low

## Storage
DR Scenario Matrix – Storage Account (fsamuatbackupsa)
Step 3 ¦ Backup: RSV-managed + ZRS ¦ Freq: Daily full, incremental ¦ Dep: Step 2
# | Disaster Scenario | Severity | Likelihood | Impact | Detection Method | Terraform DR Action | Manual Steps (if any) | RTO Target | Runbook Dep
1 | Storage account fsamuatbackupsa accidentally deleted | Critical | Low | RSV backup staging area gone; active backup jobs fail; NSG flow logs lost | storage-availability-drop alert fires; RSV backup jobs error with storage reference failure | terraform apply recreates storage account with ZRS replication and lifecycle policy | Re-link RSV to new storage account in Azure portal. Re-enable NSG flow logs. | 20 min | Step 2
2 | Storage replication downgraded from ZRS to LRS | High | Medium | Backup staging data not zone-redundant; single-zone failure causes data loss | terraform plan shows drift on account_replication_type | terraform apply enforces ZRS replication on existing storage account | None – Terraform corrects drift automatically. | 10 min | Step 2
3 | Backup staging container deleted | High | Medium | RSV has nowhere to stage backup data; incremental backup jobs fail | RSV backup job errors; az storage container list shows container missing | terraform apply recreates azurerm_storage_container.backup_container | Trigger manual RSV backup job after container is restored. | 10 min | Step 2
4 | Lifecycle management policy removed — backup blobs not tiered/deleted | Medium | Medium | Storage costs grow unbounded; old backup data never archived or deleted | terraform plan shows lifecycle policy missing; storage cost spike in Azure Cost Management | terraform apply re-creates azurerm_storage_management_policy.backup_lifecycle | None – Terraform corrects drift automatically. | 5 min | Step 2
5 | Storage account public access accidentally enabled | High | High | Backup staging data exposed publicly; compliance violation | Azure Defender for Storage alert; terraform plan shows drift on public access setting | terraform apply re-enforces allow_nested_items_to_be_public = false | Run az storage account update to disable public access immediately as emergency fix. | 5 min | Step 2
SEVERITY LEGEND
Critical
High
Medium
Low

## Network
DR Scenario Matrix – Virtual Network / NSGs / NICs (fsamuat-vnet)
Step 4 ¦ Backup: ARM/Bicep IaC + NSG flow log export ¦ Freq: On-change ¦ Dep: Step 3
# | Disaster Scenario | Severity | Likelihood | Impact | Detection Method | Terraform DR Action | Manual Steps (if any) | RTO Target | Runbook Dep
1 | VNet fsamuat-vnet accidentally deleted | Critical | Low | All VM NICs, subnets, NSGs, and private endpoints lose network connectivity | VM heartbeat alert fires; LB health probe fails; all services unreachable | terraform apply recreates VNet, subnets, and NSG associations. PE and NIC must be re-attached. | Re-attach VM NIC to new subnet. Re-create private endpoints. Verify effective routes on NIC. | 1 hr | Step 3
2 | NSG rule blocking SQL port 1433 added incorrectly | High | High | App cannot reach SQL Server; DB connection fails across all app instances | App DB timeout errors; NSG flow logs show DENY on port 1433 | terraform apply re-applies correct NSG rules defined in step4_network.tf | Remove blocking rule immediately via: az network nsg rule delete. | 15 min | Step 3
3 | NSG flow logs disabled — no network visibility | Medium | Medium | Loss of network traffic audit trail; DR investigation blind | terraform plan shows flow log missing; Log Analytics stops receiving NSG events | terraform apply re-creates azurerm_network_watcher_flow_log.nsg_flow_log | None – Terraform corrects drift automatically. | 10 min | Step 3
4 | VM NIC detached or deleted | Critical | Medium | VM loses all network connectivity; app unreachable; backup agent cannot communicate | VM heartbeat missing alert fires; LB DipAvailability < 100% | terraform apply re-creates NIC and re-attaches to app-subnet. LB backend pool association restored. | Restart VM after NIC re-attachment. Verify IP assignment and effective routes. | 30 min | Step 3
5 | Subnet app-subnet address prefix changed | High | Low | VM and PE IP addresses shift; DNS resolution breaks; KV PE unreachable | Private endpoint connectivity fails; app KV secret fetch returns timeout | terraform apply re-enforces correct subnet address prefix | Re-register private DNS zone link. Verify PE DNS resolution from VM. | 30 min | Step 3
6 | Network Watcher deleted — NSG flow logs stop | Medium | Low | NSG flow logs cannot be created without Network Watcher; compliance gap | Flow log creation fails with 'NetworkWatcher not found' error | terraform apply recreates azurerm_network_watcher.nw in the region | None – Terraform corrects drift automatically. | 10 min | Step 3
SEVERITY LEGEND
Critical
High
Medium
Low

## VM_Disks
DR Scenario Matrix – VM OS Disk C:\ + Data Disk E:\ (fsam-uat-vm)
Steps 5+6 ¦ Backup: Azure VM Backup via RSV (crash+app-consistent) ¦ Freq: Daily ¦ Dep: Step 4/5
# | Disaster Scenario | Severity | Likelihood | Impact | Detection Method | Terraform DR Action | Manual Steps (if any) | RTO Target | Runbook Dep
1 | VM fsam-uat-vm accidentally deleted | Critical | Low | Full application outage; OS disk C:\ and data disk E:\ may be detached | VM heartbeat missing alert fires immediately; LB DipAvailability drops to 0% | terraform apply re-registers VM in RSV. Restore VM from RSV backup via: az backup restore restore-disks | Restore VM from latest RSV restore point. Re-attach data disk E:\. Re-bind IIS SSL cert. | 20 min | Step 4
2 | VM backup protection removed from RSV | Critical | Medium | VM no longer backed up; OS and data disk snapshots stop; RPO gap grows | RSV backup items list no longer shows fsam-uat-vm; no new restore points created | terraform apply re-registers: azurerm_backup_protected_vm.vm_backup | Trigger immediate manual backup after re-registration to close RPO gap. | 10 min | Step 4
3 | OS disk C:\ corrupted (app-consistent snapshot needed) | Critical | Medium | OS fails to boot; application completely down | VM heartbeat alert fires; RDP/SSH connection fails | Restore from latest app-consistent RSV snapshot. terraform apply re-registers VM in RSV after restore. | az backup restore restore-disks → swap OS disk → start VM → verify IIS and SQL agent. | 20 min | Step 4
4 | Data disk E:\ corrupted or accidentally formatted | Critical | Medium | Application data loss; DB files on E:\ inaccessible | SQL Server errors; app logs show data file access failures | Restore data disk from RSV snapshot (disk snapshot included in VM backup job — Step 6). | az backup restore restore-disks → detach corrupted E:\ → attach restored disk → restart SQL. | 20 min | Step 5
5 | VM backup policy changed to weekly (less frequent than daily) | High | Medium | RPO increases from 24 hrs to 7 days; significant potential data loss window | terraform plan shows drift on backup policy frequency | terraform apply re-enforces daily backup policy: azurerm_backup_policy_vm.vm_daily_policy | None – Terraform corrects drift automatically. | 5 min | Step 4
6 | VM stopped/deallocated — backup agent goes offline | Medium | High | Backup jobs fail while VM is stopped; restore points stop being created | RSV backup job shows warning: VM not running; heartbeat alert fires | No Terraform action — start VM. terraform apply verifies backup registration is intact. | Start VM: az vm start --name fsam-uat-vm --resource-group FSAM-UAT-RG | 5 min | Step 4
7 | Azure Monitor Agent on VM stops running | Medium | High | VM metrics and logs stop flowing to Log Analytics; monitoring goes blind | Heartbeat alert fires after 5-min gap; DCR association shows no data | terraform apply re-deploys AzureMonitorWindowsAgent VM extension | Verify agent: Get-Service -Name AzureMonitorAgent on VM after extension re-deploy. | 15 min | Step 8
SEVERITY LEGEND
Critical
High
Medium
Low

## LoadBalancer
DR Scenario Matrix – Load Balancer (fsamuat-lb)
Step 7 ¦ Backup: ARM/Bicep IaC + LB config export ¦ Freq: On-change ¦ Dep: Step 6
# | Disaster Scenario | Severity | Likelihood | Impact | Detection Method | Terraform DR Action | Manual Steps (if any) | RTO Target | Runbook Dep
1 | Load Balancer fsamuat-lb accidentally deleted | Critical | Low | All inbound traffic to app stops; public IP unreachable | LB DipAvailability and VipAvailability alerts fire; app returns connection refused | terraform apply recreates LB from IaC definition (ARM/Bicep config). Public IP and backend pool restored. | Re-associate VM NIC with backend pool. Verify health probe returns 200 on /health. | 15 min | Step 6
2 | Health probe misconfigured — backend marked unhealthy | High | High | LB stops routing traffic to VM even though VM is healthy | lb-backend-unhealthy alert fires; DipAvailability < 100% | terraform apply re-enforces correct health probe config (HTTPS port 443 /health) | None – Terraform corrects drift automatically. | 10 min | Step 6
3 | Backend pool VM association removed | Critical | Medium | LB has no backends; all traffic returns 502/503 | DipAvailability = 0%; lb-backend-unhealthy alert fires | terraform apply re-creates NIC-to-backend-pool association | None – Terraform corrects drift automatically. | 10 min | Step 6
4 | LB frontend IP changed / public IP deleted | High | Low | DNS records point to old IP; app unreachable externally | lb-vip-unavailable alert fires; external connectivity check fails | terraform apply restores public IP and frontend IP configuration | Update DNS A record to new public IP after restore. | 20 min | Step 6
5 | LB diagnostic logs to Log Analytics disabled | Low | Medium | Loss of LB traffic audit trail; DR investigation blind | terraform plan shows diagnostic setting missing | terraform apply re-creates azurerm_monitor_diagnostic_setting.lb_diag | None – Terraform corrects drift automatically. | 5 min | Step 6
SEVERITY LEGEND
Critical
High
Medium
Low

## SSL_Certificate
DR Scenario Matrix – SSL Certificate (fsamuat-kvprivatebmw)
Step 8 ¦ Backup: KV certificate versioning + manual IIS binding ¦ Freq: Manual ¦ Dep: Step 7
# | Disaster Scenario | Severity | Likelihood | Impact | Detection Method | Terraform DR Action | Manual Steps (if any) | RTO Target | Runbook Dep
1 | SSL certificate expires — IIS HTTPS binding fails | Critical | Medium | HTTPS traffic returns SSL error; browsers block access; app unusable | ssl-cert-expiry-30days alert fires 30 days before expiry | No Terraform action — cert renewal is manual. Alert gives 30-day warning window. | Renew cert in KV: az keyvault certificate create. Re-bind to IIS on VM (PowerShell steps in step8 output). | Manual – 1 hr | Step 7
2 | SSL certificate deleted from Key Vault | Critical | Low | IIS cannot find cert for HTTPS binding; HTTPS traffic fails | IIS error logs; Invoke-WebRequest to HTTPS returns SSL handshake failure | KV auto-versions certs. If deleted, restore from KV soft-delete: az keyvault certificate recover | Re-bind recovered cert to IIS after KV restore. | 15 min | Step 7
3 | IIS HTTPS binding removed on VM | High | Medium | HTTPS traffic stops; HTTP only (insecure); compliance violation | External connectivity check fails on port 443; LB health probe fails | No Terraform action — IIS binding is manual. Runbook step8 output provides PowerShell commands. | Run IIS re-bind PowerShell on VM: Get-ChildItem Cert:\LocalMachine\My → AddSslCertificate | 20 min | Step 7
4 | KV certificate auto-renewal fails | High | Low | Cert silently expires without renewal; HTTPS outage on expiry date | ssl-cert-expiry-30days alert fires; KV cert lifetime action shows failure | Alert fires automatically. No Terraform action. | Manually trigger renewal: az keyvault certificate create. Check issuer connectivity. | 1 hr | Step 7
5 | Certificate thumbprint mismatch after renewal | Medium | Low | IIS still bound to old thumbprint; new cert not active | IIS serves expired cert despite new cert existing in KV | No Terraform action — re-binding is manual. | Re-bind new cert thumbprint to IIS site (step8 PowerShell output). | 20 min | Step 7
SEVERITY LEGEND
Critical
High
Medium
Low

## Monitoring
DR Scenario Matrix – Monitoring & Alerting (fsamuat-law)
Step 9 ¦ Backup: Azure Monitor native (always-on) + Log Analytics ¦ Freq: Real-time ¦ Dep: Step 8
# | Disaster Scenario | Severity | Likelihood | Impact | Detection Method | Terraform DR Action | Manual Steps (if any) | RTO Target | Runbook Dep
1 | Log Analytics Workspace fsamuat-law deleted | Critical | Low | All monitoring goes blind; no alerts fire; no logs; DR investigation impossible | All metric alerts stop firing; DCR association breaks; heartbeat disappears | terraform apply recreates LAW (data block reads it; if truly deleted, TF recreates as resource) | Re-associate DCR with VM. Re-deploy Monitor Agent extension. Backfill alert rules. | 30 min | Step 8
2 | Action Group fsamuat-infra-alerts deleted | High | Medium | Alerts fire in Azure Monitor but no notifications sent to infra team | Alert rules show 'action group not found'; no emails received during incident | terraform apply recreates azurerm_monitor_action_group.infra_ag with correct email | None – Terraform corrects drift automatically. | 5 min | Step 8
3 | All metric alert rules deleted | High | Low | No automated detection for VM down, LB failure, KV outage, storage drop | No alerts fire during a real incident; discovered only during DR drill | terraform apply recreates all azurerm_monitor_metric_alert and scheduled query alert rules | None – Terraform corrects drift automatically. | 10 min | Step 8
4 | Data Collection Rule dissociated from VM | Medium | Medium | VM perf counters and event logs stop flowing to Log Analytics | Heartbeat alert fires after 5 min; LAW queries return no VM data | terraform apply re-creates azurerm_monitor_data_collection_rule_association.vm_dcr_assoc | Verify data flow after reassociation: Heartbeat ¦ where Computer == 'fsam-uat-vm' | 10 min | Step 8
5 | Azure Monitor Agent extension removed from VM | Medium | Medium | VM metrics stop; heartbeat disappears; monitoring blind for that VM | Heartbeat missing alert fires after 5 min | terraform apply re-deploys AzureMonitorWindowsAgent VM extension | Verify: Get-Service -Name AzureMonitorAgent on VM. | 15 min | Step 8
SEVERITY LEGEND
Critical
High
Medium
Low

## External
DR Scenario Matrix – External Connectivity (Vertex / AWS Cognito / AWS API)
Step 9b ¦ No backup/restore – connectivity verify only ¦ Freq: N/A ¦ Dep: Step 9
# | Disaster Scenario | Severity | Likelihood | Impact | Detection Method | Terraform DR Action | Manual Steps (if any) | RTO Target | Runbook Dep
1 | Outbound HTTPS to AWS Cognito blocked by NSG | High | Medium | Authentication via Cognito fails; users cannot log in to app | external-connectivity-failure alert fires; Invoke-WebRequest to Cognito returns timeout | terraform apply re-enforces NSG outbound rules allowing port 443 to Internet | Test: Invoke-WebRequest https://cognito-idp.us-east-1.amazonaws.com from VM. | 15 min | Step 9
2 | Outbound HTTPS to Vertex AI (GCP) blocked | High | Medium | AI/ML inference calls from app fail; feature degradation | external-connectivity-failure alert fires; app logs show Vertex API timeout | terraform apply re-enforces outbound NSG rule for port 443 | Test: Invoke-WebRequest https://aiplatform.googleapis.com from VM. | 15 min | Step 9
3 | Outbound HTTPS to AWS API Gateway blocked | High | Medium | Backend API calls to AWS services fail; partial app functionality lost | external-connectivity-failure alert fires; app logs show AWS API connection refused | terraform apply re-enforces outbound NSG rule for port 443 | Test: Invoke-WebRequest https://execute-api.us-east-1.amazonaws.com from VM. | 15 min | Step 9
4 | External service (Vertex/Cognito/AWS) itself goes down | Medium | Low | App features dependent on external service degrade; not an Azure-side issue | external-connectivity-failure alert fires but NSG shows no DENY rules | No Terraform action — external service outage outside Azure control. | Monitor external service status pages. Implement circuit breaker in app if not present. | Dep on vendor | Step 9
SEVERITY LEGEND
Critical
High
Medium
Low