## Prod Azure DR Summary
DISASTER RECOVERY PLAN – FSAM PROD ¦ Executive Summary
Resource Group: FSAM-PROD-RG ¦ Region: East US ¦ RSV: fsamprod-rsv ¦ Serial Execution ¦ Total Steps: 19 ¦ Total RTO: ~9.5 hrs
# Component | Backup & Restore Method | Restore Time (min) | Backup Frequency | Dependency (Prior Step)
▶ PHASE 1 – INFRASTRUCTURE (Steps 1–9)
1 – Recovery Services Vault – Verify | Azure Backup built-in RSV verification (pre-flight check – no restore action) | 13 | N/A – Pre-check | None – DR Start
2 – Key Vault – Secrets & Access | Azure Key Vault soft-delete + purge-protection (geo-redundant, auto-replication) | 13 | Continuous (geo-redundant replication) | Step 1
3 – Storage Account – Backup Staging | Azure Backup staging (RSV-managed) + Azure Storage geo-redundancy (ZRS) | 13 | Matches RSV policy (daily full, incremental) | Step 2
4 – Virtual Network, NSGs & NICs | ARM template / Bicep IaC (versioned in source control) + NSG flow log export | 20 | On-change (IaC pipeline deploy) | Step 3
5 – VM OS Disk C:\ – Health Check (VM Running) | Azure VM Backup via RSV (crash-consistent + app-consistent snapshots) | 26 | Daily (RSV VM backup policy) | Step 4
6 – VM Data Disk E:\ – Health Check (VM Running) | Azure VM Backup via RSV (disk snapshot included in VM backup job) | 26 | Daily (RSV VM backup policy) | Step 5
7 – Load Balancer – Health Verify | ARM template / Bicep IaC + Azure LB config export (no restore – verify only) | 13 | On-change (IaC pipeline) | Step 6
8 – SSL Certificate – Verify & Bind | Azure Key Vault certificate versioning + manual IIS HTTPS binding | 13 | Manual (certificate renewal cycle) | Step 7
9 – Monitoring & Alerting – Verify Active | Azure Monitor native (always-on, no restore needed) + Log Analytics verification | 13 | Real-time (continuous ingestion) | Step 8
9b – PROD Interfaces – External Connectivity Verify | No backup/restore – external services (Vertex, AWS Cognito, AWS API). Connectivity verify only. | 20 | N/A – External services | Step 9
▶ PHASE 2 – DATABASE (Steps 10–15)
10 – SQL Server Service – Start & Config Verify | Windows Service auto-start config; SQL Server service account stored in KV | 13 | N/A – Service config (on-change) | Step 9b
11 – SQL Server Agent – Suspend Before Restore | SQL Agent job scripts exported to source control; jobs suspended before restore | 13 | On-change (job scripts versioned) | Step 10
12 – SQL Database (sfam_prod_db) – Full Restore from RSV | Azure Backup for SQL Server in Azure VM (RSV-native); Full → Diff → Log chain; PITR supported | 156 | Full: Weekly ¦ Differential: Daily ¦ Transaction Log: every 15–60 min | Step 11
13 – SQL Logins, Users & Permissions – Re-map | SQL scripts in source control (logins_permissions.sql); manual re-map post-restore | 26 | On-change (after any permission modification) | Step 12
14 – SQL Database Integrity & Validation (DBCC) | Manual T-SQL validation (DBCC CHECKDB) + DMV queries for performance baseline | 39 | Post-restore (one-time validation) | Step 13
15 – SQL Agent Jobs – Re-enable Post-Restore | SQL Agent job scripts from source control; manual re-enablement via T-SQL / SSMS | 13 | Post-restore (re-enablement) | Step 14
▶ PHASE 3 – APPLICATION (Steps 16–19)
16 – Application Config & Connection Strings | Azure Key Vault secret versioning + Managed Identity for secretless authentication | 26 | On-change (KV secrets versioned) | Step 15
17 – C:\ & E:\ Drive App Files – Verify & Restore | Azure VM Backup via RSV (crash-consistent); RSV file-level restore; Azure File Share (sfam-prod) | 39 | Daily (RSV VM backup – both C:\ and E:\ disks captured) | Step 16
18 – Application Services – Restart & Health Check | Application deployment pipeline (CI/CD) + Windows Service / IIS restart + App team runbook | 39 | On-change (deployment pipeline) | Step 17
19 – End-to-End Validation & Stakeholder Sign-off | Manual testing + automated smoke test suite + post-DR report to stakeholders | 39 | Post-restore (one-time) | Step 18
GRAND TOTAL – Full Serial DR Restore (19 Steps) |  | 573 | Full: Weekly ¦ Diff: Daily ¦ Log: every 15–60 min | –

## Prod Azure Backup Cost Summary
BMW FS Azure Recovery Services Vault — PROD Cost Analysis (Projected)
Data as of April 2, 2026 ¦ Resource Type: microsoft.recoveryservices/vaults ¦ All costs in USD ¦ PROD projection: +30% scale uplift
Subscription | Per Day (30-day avg) | Per Week (7-day actual) | Per Month (Actual) | Per Month (Projected) | Annual Total (Historical) | Annual (Projected) | Data Range
FS-AM-CMS-AF-PROD | 26.56 | 213.96 | 813.98 | 808.46 | 2143.93 | 9694.07 | 12 months (monthly) + 30d daily
TOTAL — PROD SUBSCRIPTION | 26.56 | 213.96 | 813.98 | 808.46 | 2143.93 | 9694.07
📌 NOTES:
• Per Day = 30-day rolling average from actual daily spend (Mar 4 – Apr 2, 2026)
• Per Week = Actual 7-day spend (Mar 27 – Apr 2, 2026)
• Per Month (Actual) = Actual March 2026 cost from monthly billing data
• Per Month (Projected) = Per Day avg × 30.44 days
• Annual Total (Historical) = Sum of all available monthly billing data
• Annual (Projected) = Per Day avg × 365 days
• PROD projection reflects +30% scale uplift over baseline Azure Backup cost pattern
• Actual PROD costs will depend on VM count, retention policy, data change rate, and region pricing