## Summary
CCG Terraform Plan Analysis
Environment: FSAM-CLEANCONFIG-RG ¦ Subscription: 4cda8977-68ea-4ca5-aa6a-fae45e7e98f3 ¦ Generated: 2026-04-10
Plan Summary
Total to Add | 26
Total to Change | 14
Total to Destroy | 2
Total Actions | 42
Resource Groups Involved
Resource Group | Role | Subscription ID | Changes Applied
FSAM-CLEANCONFIG-RG | PRIMARY — all creates/updates/destroys here | 4cda8977-68ea-4ca5-aa6a-fae45e7e98f3 | Yes
RG-VNET-SPOKE-EUS-12815 | READ-ONLY — referenced for VNET/Subnet-1 only | 4cda8977-68ea-4ca5-aa6a-fae45e7e98f3 | No
Action Type Breakdown
Action | Count | Description | Azure Impact | Status
REPLACE | 2 | Destroyed then recreated in Azure | ⚠ HIGH — brief downtime | ❌ Not yet fixed
CREATE | 26 | New resources added to Terraform state | MEDIUM — 7 real Azure, 19 internal | ⚠ Partial (3 suppressed)
UPDATE | 14 | In-place changes to existing resources | LOW — no destroy/recreate | ⚠ Partial
READ | 1 | Data source read (no Azure change) | NONE | ✅ No action needed

## All Plan Changes
All Terraform Plan Changes — CCG Environment ¦ Plan: 26 to add, 14 to change, 2 to destroy
# | Action | Priority | Resource Type | Terraform Address | Applies To | Resource Group | In State? | Changed Fields / Root Cause | Fix / Notes
1 | CREATE | HIGH | azurerm_network_interface_backend_address_pool_association | module.application_load_balancer.azurerm_network_interface_backend_address_pool_association.lb_backend_assoc["fs-ccg-web1"] | fs-ccg-web1 | FSAM-CLEANCONFIG-RG | No | Not in state — NIC-to-LB association | Set backend_nics = {} in network.tf — suppressed in v3
2 | CREATE | HIGH | azurerm_network_interface_backend_address_pool_association | module.application_load_balancer.azurerm_network_interface_backend_address_pool_association.lb_backend_assoc["fs-ccg-web2"] | fs-ccg-web2 | FSAM-CLEANCONFIG-RG | No | Not in state — NIC-to-LB association | Set backend_nics = {} in network.tf — suppressed in v3
3 | REPLACE | CRITICAL | azurerm_application_insights | module.application_log_analytics.azurerm_application_insights.explicit_app_insights[0] | Log Analytics | FSAM-CLEANCONFIG-RG | Yes | Name drift: fsam-ccg-2-aapin → fsamccg2-aapin (module naming convention changed between versions) | Add lifecycle { ignore_changes = [name, tags] } in modules/log_analytics_workspace/main.tf — included in v3
4 | REPLACE | CRITICAL | azurerm_private_endpoint | module.application_storage_private_endpoints["file"].azurerm_private_endpoint.pe | Storage PE | FSAM-CLEANCONFIG-RG | Yes | PSC name mismatch: state=fsamccgstprivatebmw-pe-file, module generates psc-{name} | Add psc_name_override variable to private_endpoint module, set in network.tf — included in v3
5 | CREATE | LOW | random_string | module.common.random_string.random_string_global | Common module | FSAM-CLEANCONFIG-RG | No | BMW commons module (ref=2.3.0) added random_string internally | Cannot suppress — internal to external BMW module. Non-Azure resource, no infrastructure impact.
6 | READ | INFO | azurerm_client_config | module.application_key_vault.module.bmw_key_vault.data.azurerm_client_config.current | Key Vault | FSAM-CLEANCONFIG-RG | No | Data source read — triggered by KV being created | No action needed — read-only data source, no Azure change
7 | CREATE | CRITICAL | azurerm_key_vault | module.application_key_vault.module.bmw_key_vault.azurerm_key_vault.this | Key Vault | FSAM-CLEANCONFIG-RG | No (exists in Azure) | KV fsamccg2-kv exists in Azure but not in Terraform state — fresh create would fail | Add import block in imports.tf — included in v3
8 | UPDATE | MEDIUM | azurerm_log_analytics_workspace | module.application_log_analytics.module.bmw_log_analytics_workspace.azurerm_log_analytics_workspace.this | LAW | FSAM-CLEANCONFIG-RG | Yes | Tags: DeploymentTimestamp removed, BMW standard tags added (consumed_by, managed_by, owned_by, provisioned_by) | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
9 | UPDATE | HIGH | azurerm_storage_account | module.application_storage_account.module.bmw_storage_account.azurerm_storage_account.this | Storage | FSAM-CLEANCONFIG-RG | Yes | Tags + default_share_level_permission: ElevatedContributor→Contributor + network_rules (IP + subnet removed) + identity_ids | Set azure_files_default_share_level_permission=ElevatedContributor in storage module — done in v3. Network rules drift remains.
10 | CREATE | LOW | azurerm_user_assigned_identity | module.application_storage_account.module.bmw_storage_account.azurerm_user_assigned_identity.storage[0] | Storage | FSAM-CLEANCONFIG-RG | No | BMW storage module creates UAI by default (create_user_assigned_identity=true) | Set create_user_assigned_identity=false in modules/storage_account/main.tf — suppressed in v3
11 | UPDATE | MEDIUM | azurerm_network_interface | module.application_vms["fs-ccg-app1"].module.bmw_vm.azurerm_network_interface.this | fs-ccg-app1 | FSAM-CLEANCONFIG-RG | Yes | Tags: DeploymentTimestamp removed, BMW standard tags added | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
12 | CREATE | MEDIUM | azurerm_network_interface_security_group_association | module.application_vms["fs-ccg-app1"].module.bmw_vm.azurerm_network_interface_security_group_association.nsg_association | fs-ccg-app1 | FSAM-CLEANCONFIG-RG | No | Hardcoded in BMW VM module (securityfix). No variable to disable. | Pin module to ref=2.0.7 OR accept one-time create (idempotent after first apply)
13 | UPDATE | MEDIUM | azurerm_network_security_group | module.application_vms["fs-ccg-app1"].module.bmw_vm.azurerm_network_security_group.nsg[0] | fs-ccg-app1 | FSAM-CLEANCONFIG-RG | Yes | Tags: DeploymentTimestamp removed, BMW standard tags added | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
14 | CREATE | LOW | terraform_data | module.application_vms["fs-ccg-app1"].module.bmw_vm.terraform_data.only_allow_win_or_linux | fs-ccg-app1 | FSAM-CLEANCONFIG-RG | No | BMW VM module (securityfix) internal OS validation guard | Cannot suppress — internal to external BMW module. Non-Azure resource.
15 | UPDATE | MEDIUM | azurerm_network_interface | module.application_vms["fs-ccg-app2"].module.bmw_vm.azurerm_network_interface.this | fs-ccg-app2 | FSAM-CLEANCONFIG-RG | Yes | Tags: DeploymentTimestamp removed, BMW standard tags added | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
16 | CREATE | MEDIUM | azurerm_network_interface_security_group_association | module.application_vms["fs-ccg-app2"].module.bmw_vm.azurerm_network_interface_security_group_association.nsg_association | fs-ccg-app2 | FSAM-CLEANCONFIG-RG | No | Hardcoded in BMW VM module (securityfix). No variable to disable. | Pin module to ref=2.0.7 OR accept one-time create
17 | UPDATE | MEDIUM | azurerm_network_security_group | module.application_vms["fs-ccg-app2"].module.bmw_vm.azurerm_network_security_group.nsg[0] | fs-ccg-app2 | FSAM-CLEANCONFIG-RG | Yes | Tags: DeploymentTimestamp removed, BMW standard tags added | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
18 | CREATE | LOW | terraform_data | module.application_vms["fs-ccg-app2"].module.bmw_vm.terraform_data.only_allow_win_or_linux | fs-ccg-app2 | FSAM-CLEANCONFIG-RG | No | BMW VM module internal validation guard | Cannot suppress — internal to external BMW module
19 | UPDATE | MEDIUM | azurerm_network_interface | module.application_vms["fs-ccg-web1"].module.bmw_vm.azurerm_network_interface.this | fs-ccg-web1 | FSAM-CLEANCONFIG-RG | Yes | Tags: DeploymentTimestamp removed, BMW standard tags added | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
20 | CREATE | MEDIUM | azurerm_network_interface_security_group_association | module.application_vms["fs-ccg-web1"].module.bmw_vm.azurerm_network_interface_security_group_association.nsg_association | fs-ccg-web1 | FSAM-CLEANCONFIG-RG | No | Hardcoded in BMW VM module (securityfix). No variable to disable. | Pin module to ref=2.0.7 OR accept one-time create
21 | UPDATE | MEDIUM | azurerm_network_security_group | module.application_vms["fs-ccg-web1"].module.bmw_vm.azurerm_network_security_group.nsg[0] | fs-ccg-web1 | FSAM-CLEANCONFIG-RG | Yes | Tags: DeploymentTimestamp removed, BMW standard tags added | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
22 | CREATE | LOW | terraform_data | module.application_vms["fs-ccg-web1"].module.bmw_vm.terraform_data.only_allow_win_or_linux | fs-ccg-web1 | FSAM-CLEANCONFIG-RG | No | BMW VM module internal validation guard | Cannot suppress — internal to external BMW module
23 | UPDATE | MEDIUM | azurerm_network_interface | module.application_vms["fs-ccg-web2"].module.bmw_vm.azurerm_network_interface.this | fs-ccg-web2 | FSAM-CLEANCONFIG-RG | Yes | Tags: DeploymentTimestamp removed, BMW standard tags added | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
24 | CREATE | MEDIUM | azurerm_network_interface_security_group_association | module.application_vms["fs-ccg-web2"].module.bmw_vm.azurerm_network_interface_security_group_association.nsg_association | fs-ccg-web2 | FSAM-CLEANCONFIG-RG | No | Hardcoded in BMW VM module (securityfix). No variable to disable. | Pin module to ref=2.0.7 OR accept one-time create
25 | UPDATE | MEDIUM | azurerm_network_security_group | module.application_vms["fs-ccg-web2"].module.bmw_vm.azurerm_network_security_group.nsg[0] | fs-ccg-web2 | FSAM-CLEANCONFIG-RG | Yes | Tags: DeploymentTimestamp removed, BMW standard tags added | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
26 | CREATE | LOW | terraform_data | module.application_vms["fs-ccg-web2"].module.bmw_vm.terraform_data.only_allow_win_or_linux | fs-ccg-web2 | FSAM-CLEANCONFIG-RG | No | BMW VM module internal validation guard | Cannot suppress — internal to external BMW module
27 | CREATE | LOW | random_string | module.application_key_vault.module.bmw_key_vault.module.common.random_string.random_string_global | Key Vault | FSAM-CLEANCONFIG-RG | No | BMW commons module internal — added in newer module version | Cannot suppress — internal to external BMW module. Non-Azure.
28 | CREATE | LOW | random_string | module.application_log_analytics.module.bmw_log_analytics_workspace.module.common.random_string.random_string_global | Log Analytics | FSAM-CLEANCONFIG-RG | No | BMW commons module internal | Cannot suppress — internal to external BMW module. Non-Azure.
29 | CREATE | LOW | random_string | module.application_storage_account.module.bmw_storage_account.module.common.random_string.random_string_global | Storage | FSAM-CLEANCONFIG-RG | No | BMW commons module internal | Cannot suppress — internal to external BMW module. Non-Azure.
30 | CREATE | LOW | random_string | module.application_vms["fs-ccg-app1"].module.bmw_vm.module.common.random_string.random_string_global | fs-ccg-app1 | FSAM-CLEANCONFIG-RG | No | BMW commons module internal | Cannot suppress — internal to external BMW module. Non-Azure.
31 | UPDATE | HIGH | azurerm_windows_virtual_machine | module.application_vms["fs-ccg-app1"].module.bmw_vm.module.windows_vm[0].azurerm_windows_virtual_machine.this | fs-ccg-app1 | FSAM-CLEANCONFIG-RG | Yes | proximity_placement_group_id removed → null; tags drift; Environment casing ccg→CCG | Pass proximity_placement_group_id in vm.tf; remove timestamp from merged_tags — in v3
32 | CREATE | LOW | random_string | module.application_vms["fs-ccg-app2"].module.bmw_vm.module.common.random_string.random_string_global | fs-ccg-app2 | FSAM-CLEANCONFIG-RG | No | BMW commons module internal | Cannot suppress — non-Azure.
33 | UPDATE | HIGH | azurerm_windows_virtual_machine | module.application_vms["fs-ccg-app2"].module.bmw_vm.module.windows_vm[0].azurerm_windows_virtual_machine.this | fs-ccg-app2 | FSAM-CLEANCONFIG-RG | Yes | proximity_placement_group_id removed → null; tags drift | Pass proximity_placement_group_id in vm.tf; remove timestamp from merged_tags — in v3
34 | CREATE | LOW | random_string | module.application_vms["fs-ccg-web1"].module.bmw_vm.module.common.random_string.random_string_global | fs-ccg-web1 | FSAM-CLEANCONFIG-RG | No | BMW commons module internal | Cannot suppress — non-Azure.
35 | UPDATE | HIGH | azurerm_windows_virtual_machine | module.application_vms["fs-ccg-web1"].module.bmw_vm.module.windows_vm[0].azurerm_windows_virtual_machine.this | fs-ccg-web1 | FSAM-CLEANCONFIG-RG | Yes | proximity_placement_group_id removed → null; tags drift | Pass proximity_placement_group_id in vm.tf; remove timestamp from merged_tags — in v3
36 | CREATE | LOW | random_string | module.application_vms["fs-ccg-web2"].module.bmw_vm.module.common.random_string.random_string_global | fs-ccg-web2 | FSAM-CLEANCONFIG-RG | No | BMW commons module internal | Cannot suppress — non-Azure.
37 | UPDATE | HIGH | azurerm_windows_virtual_machine | module.application_vms["fs-ccg-web2"].module.bmw_vm.module.windows_vm[0].azurerm_windows_virtual_machine.this | fs-ccg-web2 | FSAM-CLEANCONFIG-RG | Yes | proximity_placement_group_id removed → null; tags drift | Pass proximity_placement_group_id in vm.tf; remove timestamp from merged_tags — in v3
38 | CREATE | LOW | random_string | module.application_vms["fs-ccg-app1"].module.bmw_vm.module.windows_vm[0].module.common.random_string.random_string_global | fs-ccg-app1 | FSAM-CLEANCONFIG-RG | No | BMW nested commons module internal | Cannot suppress — non-Azure.
39 | CREATE | LOW | random_string | module.application_vms["fs-ccg-app2"].module.bmw_vm.module.windows_vm[0].module.common.random_string.random_string_global | fs-ccg-app2 | FSAM-CLEANCONFIG-RG | No | BMW nested commons module internal | Cannot suppress — non-Azure.
40 | CREATE | LOW | random_string | module.application_vms["fs-ccg-web1"].module.bmw_vm.module.windows_vm[0].module.common.random_string.random_string_global | fs-ccg-web1 | FSAM-CLEANCONFIG-RG | No | BMW nested commons module internal | Cannot suppress — non-Azure.
41 | CREATE | LOW | random_string | module.application_vms["fs-ccg-web2"].module.bmw_vm.module.windows_vm[0].module.common.random_string.random_string_global | fs-ccg-web2 | FSAM-CLEANCONFIG-RG | No | BMW nested commons module internal | Cannot suppress — non-Azure.

## REPLACE — Destroy+Recreate
⚠ REPLACE — Resources that will be DESTROYED then RECREATED in Azure
# | Resource Type | Terraform Address | Applies To | Root Cause (Force Replacement) | Fix Required | Status
1 | azurerm_application_insights | module.application_log_analytics.azurerm_application_insights.explicit_app_insights[0] | Log Analytics | name: fsam-ccg-2-aapin → fsamccg2-aapin — module regenerates a different name. Any name change forces destroy+recreate. | Add lifecycle { ignore_changes = [name, tags] } in modules/log_analytics_workspace/main.tf | ✅ Fix included in v3
2 | azurerm_private_endpoint | module.application_storage_private_endpoints["file"].azurerm_private_endpoint.pe | Storage PE | PSC name mismatch: state = "fsamccgstprivatebmw-pe-file", module generates "psc-fsamccgstprivatebmw-pe-file". PSC name change forces PE replacement. | Add psc_name_override variable to private_endpoint module; set psc_name_override = base_name in network.tf | ✅ Fix included in v3

## CREATE
CREATE — New resources Terraform plans to add (26 total)
# | Resource Type | Terraform Address | Applies To | In State? | Reason / Root Cause | Fix / Suppression Status
1 | azurerm_network_interface_backend_address_pool_association | lb_backend_assoc["fs-ccg-web1"] | fs-ccg-web1 | No | NIC-to-LB backend pool association — not in state | ✅ SUPPRESSED — backend_nics = {} in network.tf (v3)
2 | azurerm_network_interface_backend_address_pool_association | lb_backend_assoc["fs-ccg-web2"] | fs-ccg-web2 | No | NIC-to-LB backend pool association — not in state | ✅ SUPPRESSED — backend_nics = {} in network.tf (v3)
3 | azurerm_key_vault | module.application_key_vault...azurerm_key_vault.this | Key Vault | No (exists in Azure) | KV fsamccg2-kv exists in Azure but not in Terraform state. Fresh create would fail. | ⚠ Import block added in imports.tf (v3)
4 | azurerm_user_assigned_identity | ...bmw_storage_account.azurerm_user_assigned_identity.storage[0] | Storage | No | BMW storage module creates UAI by default (create_user_assigned_identity=true) | ✅ SUPPRESSED — create_user_assigned_identity=false in storage module (v3)
5 | azurerm_network_interface_security_group_association | ...fs-ccg-app1...nsg_association | fs-ccg-app1 | No | Hardcoded inside BMW VM module (securityfix branch). No variable to disable. | ❌ CANNOT SUPPRESS — Pin module to ref=2.0.7 to eliminate
6 | azurerm_network_interface_security_group_association | ...fs-ccg-app2...nsg_association | fs-ccg-app2 | No | Hardcoded inside BMW VM module (securityfix branch). No variable to disable. | ❌ CANNOT SUPPRESS — Pin module to ref=2.0.7
7 | azurerm_network_interface_security_group_association | ...fs-ccg-web1...nsg_association | fs-ccg-web1 | No | Hardcoded inside BMW VM module (securityfix branch). No variable to disable. | ❌ CANNOT SUPPRESS — Pin module to ref=2.0.7
8 | azurerm_network_interface_security_group_association | ...fs-ccg-web2...nsg_association | fs-ccg-web2 | No | Hardcoded inside BMW VM module (securityfix branch). No variable to disable. | ❌ CANNOT SUPPRESS — Pin module to ref=2.0.7
9 | terraform_data | ...fs-ccg-app1...only_allow_win_or_linux | fs-ccg-app1 | No | BMW VM module (securityfix) internal OS validation guard. Non-Azure. | ❌ CANNOT SUPPRESS — Pin to ref=2.0.7. Non-Azure, no infra impact.
10 | terraform_data | ...fs-ccg-app2...only_allow_win_or_linux | fs-ccg-app2 | No | BMW VM module internal validation guard. Non-Azure. | ❌ CANNOT SUPPRESS — Non-Azure, no impact
11 | terraform_data | ...fs-ccg-web1...only_allow_win_or_linux | fs-ccg-web1 | No | BMW VM module internal validation guard. Non-Azure. | ❌ CANNOT SUPPRESS — Non-Azure, no impact
12 | terraform_data | ...fs-ccg-web2...only_allow_win_or_linux | fs-ccg-web2 | No | BMW VM module internal validation guard. Non-Azure. | ❌ CANNOT SUPPRESS — Non-Azure, no impact
13 | random_string | module.common.random_string.random_string_global | Common | No | BMW commons (ref=2.3.0) added random_string internally. Non-Azure. | ❌ CANNOT SUPPRESS — Non-Azure, no infra impact
14 | random_string | ...bmw_key_vault.module.common.random_string... | Key Vault | No | BMW KV module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS — Non-Azure
15 | random_string | ...bmw_log_analytics_workspace.module.common.random_string... | Log Analytics | No | BMW LAW module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS — Non-Azure
16 | random_string | ...bmw_storage_account.module.common.random_string... | Storage | No | BMW storage module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS — Non-Azure
17 | random_string | ...fs-ccg-app1...bmw_vm.module.common.random_string... | fs-ccg-app1 | No | BMW VM module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS
18 | random_string | ...fs-ccg-app2...bmw_vm.module.common.random_string... | fs-ccg-app2 | No | BMW VM module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS
19 | random_string | ...fs-ccg-web1...bmw_vm.module.common.random_string... | fs-ccg-web1 | No | BMW VM module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS
20 | random_string | ...fs-ccg-web2...bmw_vm.module.common.random_string... | fs-ccg-web2 | No | BMW VM module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS
21 | random_string | ...fs-ccg-app1...windows_vm[0].module.common.random_string... | fs-ccg-app1 | No | BMW nested commons module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS
22 | random_string | ...fs-ccg-app2...windows_vm[0].module.common.random_string... | fs-ccg-app2 | No | BMW nested commons module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS
23 | random_string | ...fs-ccg-web1...windows_vm[0].module.common.random_string... | fs-ccg-web1 | No | BMW nested commons module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS
24 | random_string | ...fs-ccg-web2...windows_vm[0].module.common.random_string... | fs-ccg-web2 | No | BMW nested commons module internal random_string. Non-Azure. | ❌ CANNOT SUPPRESS
25 | azurerm_client_config | ...bmw_key_vault.data.azurerm_client_config.current | Key Vault | No | Data source read triggered by KV creation — read-only, no Azure change | ✅ No action needed — data read only

## UPDATE
UPDATE — In-place changes to existing resources (14 total) — No destroy/recreate, Azure resource stays running
# | Resource Type | Terraform Address | Applies To | Fields Changing | Root Cause | Fix
1 | azurerm_log_analytics_workspace | module.application_log_analytics.module.bmw_log_analytics_workspace.azurerm_log_analytics_workspace.this | Log Analytics | tags: DeploymentTimestamp removed, BMW standard tags added (consumed_by, managed_by, owned_by, provisioned_by) | DeploymentTimestamp from merged_tags changes every plan run. New BMW module version adds standard tags. | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
2 | azurerm_storage_account | module.application_storage_account.module.bmw_storage_account.azurerm_storage_account.this | Storage | tags + default_share_level_permission (ElevatedContributor→Contributor) + network_rules (IP 20.237.42.239 removed, subnet removed) + identity_ids + private_link_access removed | Multiple drifts: BMW module version bump changes tags and permission default; network_rules managed outside Terraform. | Set azure_files_default_share_level_permission=ElevatedContributor in storage module (v3). Network rules drift — add lifecycle ignore_changes if not TF-managed.
3 | azurerm_network_interface | module.application_vms["fs-ccg-app1"].module.bmw_vm.azurerm_network_interface.this | fs-ccg-app1 | tags: DeploymentTimestamp removed, BMW standard tags added | DeploymentTimestamp changes every run. BMW module adds new standard tags in securityfix version. | Remove DeploymentTimestamp from merged_tags in main.tf — done in v3
4 | azurerm_network_interface | module.application_vms["fs-ccg-app2"].module.bmw_vm.azurerm_network_interface.this | fs-ccg-app2 | tags: DeploymentTimestamp removed, BMW standard tags added | Same as above | Remove DeploymentTimestamp from merged_tags — done in v3
5 | azurerm_network_interface | module.application_vms["fs-ccg-web1"].module.bmw_vm.azurerm_network_interface.this | fs-ccg-web1 | tags: DeploymentTimestamp removed, BMW standard tags added + Environment: ccg→CCG | Same as above | Remove DeploymentTimestamp from merged_tags — done in v3
6 | azurerm_network_interface | module.application_vms["fs-ccg-web2"].module.bmw_vm.azurerm_network_interface.this | fs-ccg-web2 | tags: DeploymentTimestamp removed, BMW standard tags added + Environment: ccg→CCG | Same as above | Remove DeploymentTimestamp from merged_tags — done in v3
7 | azurerm_network_security_group | module.application_vms["fs-ccg-app1"].module.bmw_vm.azurerm_network_security_group.nsg[0] | fs-ccg-app1 | tags: DeploymentTimestamp removed, BMW standard tags added | DeploymentTimestamp + BMW module version bump adds standard tags | Remove DeploymentTimestamp from merged_tags — done in v3
8 | azurerm_network_security_group | module.application_vms["fs-ccg-app2"].module.bmw_vm.azurerm_network_security_group.nsg[0] | fs-ccg-app2 | tags: DeploymentTimestamp removed, BMW standard tags added | Same as above | Remove DeploymentTimestamp from merged_tags — done in v3
9 | azurerm_network_security_group | module.application_vms["fs-ccg-web1"].module.bmw_vm.azurerm_network_security_group.nsg[0] | fs-ccg-web1 | tags: DeploymentTimestamp removed, BMW standard tags added | Same as above | Remove DeploymentTimestamp from merged_tags — done in v3
10 | azurerm_network_security_group | module.application_vms["fs-ccg-web2"].module.bmw_vm.azurerm_network_security_group.nsg[0] | fs-ccg-web2 | tags: DeploymentTimestamp removed, BMW standard tags added | Same as above | Remove DeploymentTimestamp from merged_tags — done in v3
11 | azurerm_windows_virtual_machine | module.application_vms["fs-ccg-app1"].module.bmw_vm.module.windows_vm[0].azurerm_windows_virtual_machine.this | fs-ccg-app1 | proximity_placement_group_id removed → null; tags drift; Environment: ccg→CCG; consumed_by/managed_by/owned_by added | PPG not passed in code; timestamp tags; BMW securityfix adds new standard tags; Environment casing | Pass proximity_placement_group_id in vm.tf; remove timestamp from merged_tags — in v3
12 | azurerm_windows_virtual_machine | module.application_vms["fs-ccg-app2"].module.bmw_vm.module.windows_vm[0].azurerm_windows_virtual_machine.this | fs-ccg-app2 | proximity_placement_group_id removed → null; tags drift | Same as above | Same fix — in v3
13 | azurerm_windows_virtual_machine | module.application_vms["fs-ccg-web1"].module.bmw_vm.module.windows_vm[0].azurerm_windows_virtual_machine.this | fs-ccg-web1 | proximity_placement_group_id removed → null; tags drift | Same as above | Same fix — in v3
14 | azurerm_windows_virtual_machine | module.application_vms["fs-ccg-web2"].module.bmw_vm.module.windows_vm[0].azurerm_windows_virtual_machine.this | fs-ccg-web2 | proximity_placement_group_id removed → null; tags drift | Same as above | Same fix — in v3

## Action Plan
Action Plan — Steps to Resolve All Remaining Plan Issues
Step | Priority | File / Location | Action | Impact | Status | Notes
1 | 🔴 CRITICAL | modules/log_analytics_workspace/main.tf | Add lifecycle { ignore_changes = [name, tags] } to azurerm_application_insights.explicit_app_insights. Azure name is fsam-ccg-2-aapin; module now generates fsamccg2-aapin. | Eliminates 1 App Insights REPLACE — stops Azure resource being destroyed | ✅ Done (v3) | Already included in v3 package
2 | 🔴 CRITICAL | modules/private_endpoint/main.tf + variables.tf + network.tf | Add psc_name_override variable to private_endpoint module. Set psc_name_override = base_name in network.tf for storage PE. | Eliminates 1 Storage Private Endpoint REPLACE — stops PE being destroyed | ✅ Done (v3) | Already included in v3 package
3 | 🔴 CRITICAL | env/ccg/imports.tf | Add import block for Key Vault fsamccg2-kv. KV exists in Azure but is not in state — without import, apply will attempt fresh create and fail. | Stops KV creation failure on apply | ✅ Done (v3) | Import block already added in imports.tf
4 | 🟠 HIGH | env/ccg/network.tf | Set backend_nics = {} in application_load_balancer module call. LB NIC associations for web1/web2 are not in state. | Eliminates 2 CREATE for lb_backend_assoc | ✅ Done (v3) | Already suppressed in v3
5 | 🟠 HIGH | modules/storage_account/main.tf | Set create_user_assigned_identity = false. Storage UAI is not in state. | Eliminates 1 CREATE for azurerm_user_assigned_identity | ✅ Done (v3) | Already suppressed in v3
6 | 🟠 HIGH | env/ccg/vm.tf | Pass proximity_placement_group_id = fsamccg-ppg ID to all 4 VMs in application_vms module call. All 4 VMs are assigned to this PPG in Azure. | Stops proximity_placement_group_id from being removed from all 4 VMs on apply | ✅ Done (v3) | Value from state: .../proximityPlacementGroups/fsamccg-ppg
7 | 🟠 HIGH | env/ccg/main.tf | Remove DeploymentTimestamp = timestamp() and TerraformWorkspace from merged_tags. These change on every plan run. | Eliminates tag UPDATE on all 14 updated resources | ✅ Done (v3) | Already removed in v3
8 | 🟡 MEDIUM | modules/virtual_machine/main.tf | Change source from securityfix to ref=2.0.7: git::https://atc-github.azure.cloud.bmw/cgbp/terraform-azure-bmw-vm.git?ref=2.0.7 | Eliminates 4 nsg_association CREATEs + 4 terraform_data CREATEs + 8 random_string CREATEs (all from securityfix branch) | ⚠ Pending | Old ref already commented in main.tf — just swap the source line
9 | 🟡 MEDIUM | modules/storage_account/main.tf | Set azure_files_default_share_level_permission = StorageFileDataSmbShareElevatedContributor (matches Azure state). BMW module default is Contributor. | Stops default_share_level_permission UPDATE on storage account | ✅ Done (v3) | Already fixed in v3 storage module variables
10 | 🟢 LOW | Accept / No action | random_string resources (×11) inside BMW commons/LAW/KV/storage/VM modules. Non-Azure resources — no infrastructure created in Azure. | After first apply these land in state and future plans show zero diff for them | ⚠ Accept or pin module | Cannot suppress without downgrading BMW module refs
11 | 🟢 LOW | Accept / No action | terraform_data.only_allow_win_or_linux (×4) — BMW VM module internal OS type guard. Non-Azure, no infrastructure. | After first apply these land in state and future plans show zero diff | ⚠ Accept or pin module ref=2.0.7 | Eliminated if VM module ref changed to 2.0.7 (Step 8)